## Schedule
Senior Project Schdule
Task | 2013-01-14 | 2013-01-21 | 2013-01-28 | 2013-02-04 | 2013-02-11 | 2013-02-18 | 2013-02-25 | 2013-03-04 | 2013-03-11 | 2013-03-18 | 2013-03-25 | 2013-04-01 | 2013-04-08 | 2013-04-15 | 2013-04-22 | 2013-04-29 | 2013-05-06
Create Skeleton for Report
Create Project Schedule
Meet with Crane Contacts
Nail Down Requirements
Download SDK, Eclipse, Emulator
Prepare Project Budget
Set up a Repository (Git Hub)
Check Out Plug-Ins for Eclipse
Learn API for Google Maps
Learn API for Google Map Icons
Learn Java Language
Learn Eclipse
Write Beginner Android App
Write Program Code
Test Debug Code
Prelim. Design Review
First Draft Report
Final Draft Report
Synopsis
Prepare Guest List
Schedule Dry Run
Practice Dry Run
Dry Run
Signed Camera Ready Copy of Text
Presentation

## Time
Time
Dustin
Day | 2013-01-14 | 2013-01-21 | 2013-01-28 | 2013-02-04 | 2013-02-11 | 2013-02-18 | 2013-02-25 | 2013-03-04 | 2013-03-11 | 2013-03-18 | 2013-03-25 | 2013-04-01 | 2013-04-08 | 2013-04-15 | 2013-04-22 | 2013-04-29 | 2013-05-06
Monday |  |  | 7
Tuesday | 2 | 1.5
Wednesday
Thursday
Friday |  | 4
Saturday | 1
Sunday |  | 4 | 3
[16 empty] | Total | 22.5
Time
Will
Day | 2013-01-14 | 2013-01-21 | 2013-01-28 | 2013-02-04 | 2013-02-11 | 2013-02-18 | 2013-02-25 | 2013-03-04 | 2013-03-11 | 2013-03-18 | 2013-03-25 | 2013-04-01 | 2013-04-08 | 2013-04-15 | 2013-04-22 | 2013-04-29 | 2013-05-06
Monday
Tuesday
Wednesday
Thursday
Friday |  | 4
Saturday
Sunday
[16 empty] | Total | 4
Time
Engineer
Day | 2013-01-14 | 2013-01-21 | 2013-01-28 | 2013-02-04 | 2013-02-11 | 2013-02-18 | 2013-02-25 | 2013-03-04 | 2013-03-11 | 2013-03-18 | 2013-03-25 | 2013-04-01 | 2013-04-08 | 2013-04-15 | 2013-04-22 | 2013-04-29 | 2013-05-06
Monday |  |  | 0.5
Tuesday |  | 0.5
Wednesday
Thursday
Friday |  | 1
Saturday
Sunday
[16 empty] | Total | 2
[16 empty] | Total | 28.5
Note on C7: Dustin: .5 hr mtg : Kuban 1 hr schedule & report skeleton
Note on C10: Dustin: 3 hr drive time 1 hr mtg: Hardy
Note on C12: Dustin: 4 hr installing software & preparing documents
Note on C22: Dustin: 3 hr drive time 1 hr mtg: Hardy
Note on D30: Dustin: mtg w/ Kuban
Note on C31: Dustin: .5 Mtg : Kuban
Note on C34: Dustin: Meeting with Mike Hardy